Salary table

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | List from Salary and Roles | | |  |
| Name | Roll | Position | Salary / Month | Salary / Hour |
| José Soreque | Project Manager | General Manager | $ 30,000 MNX | $ 144.23 MNX |
| Mayrani Reyes | Engagement Management | External management | $ 14,161 MNX | $68.08 MNX |
| Óscar López | Analyst | Attendant | $ 9,000 MNX | $43.26 MNX |
| Erick Mejía | System Architect | Attendant | $ 20,000 MNX | $96.15 MNX |
| Mayrani Reyes | Designer 1 | Attendant | $ 6,697 MNX | $32.19 MNX |
| Erick Mejía | Designer 2 | Management and Improvement | $ 5,800 MNX | $27.88 MNX |
| Óscar López | Documenter 1 | Attendant | $ 5,000 MNX | $24.03 MNX |
| Mayrani Reyes | Documenter 2 | Management and Improvement | $ 4,600 MNX | $22.11 MNX |
| Óscar López | Programmer 1 | Attendant | $ 22,000 MNX | $105.76 MNX |
| Erick Mejía | Programmer 2 | Management and Improvement | $ 19,000 MNX | $91.34 MNX |
| Jairo Barrera | Tester | Attendant | $ 12,715 MNX | $61.12 MNX |

|  |  |  |  |
| --- | --- | --- | --- |
| Service’s list | | | |
| Service | Sponsor | Cost / Monthly | Cost / Hour |
| Light | CFE | $ 350 MNX | $ 0.57 MNX |
| Water | COMAPAM | $ 100 MNX | $ 0.16 MNX |
| Internet | Mega Cable | $ 380 MNX | $ 0.61 MNX |
| Rent | Soreque´s House | Not Apply | ( Borrowed ) |
| Bathroom | Soreque´s House | Not Apply | ( Borrowed ) |
| Cafeteria | Soreque´s House | Not Apply | ( Borrowed ) |
| Office | Classroom (UTL) | $ 462.50 MNX | $ 2.96 MNX |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Materials / Resources list | | | | |
| Resource | | Quantity | Especification | Net Cost | Cost / Hour |
| Lap-top | | 4 | Compaq  HP (Touch)  HP  Lenovo | $ 3,500 MNX  $ 7,500 MNX  $ 12,500 MNX  $ 9,000 MNX | $ 8.00 MNX  $ 8.00 MNX  $ 8.00 MNX  $ 8.00 MNX |
| Mouse | | 4 | Wired  Wireless  Wireless  Wireless | $ 100.00 MNX  $ 300.00 MNX  $ 300.00 MNX  $ 4000.00 MNX | $ 0.00 MNX (Included with the computer )  $ 0.00 MNX (Included with the computer )  $ 0.00 MNX (Included with the computer )  $ 0.00 MNX (Included with the computer ) |
| USB | | 4 | 16 GB  16 GB  16 GB  16 GB | $ 150.00 MNX  $ 150.00 MNX  $ 150.00 MNX  $ 150.00 MNX | $ 0.00 MNX (Personal product not remunerated)  $ 0.00 MNX (Personal product not remunerated)  $ 0.00 MNX (Personal product not remunerated)  $ 0.00 MNX (Producto personal no retribuible) |
| Extension | | 1 | 10 Metros | $250 MNX | $ 0.00 MNX (Borrowed) |
| Table | | 1 | Madera | $ 800 MNX | $ 0.00 MNX (Borrowed) |
| Chair | | 4 | Madera | $ 250 c/u MNX | $ 0.00 MNX (Borrowed) |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | |  | |  | | | Budget allocation | | | | | | |
| Phase | Activity | | **Attendant** / Participants | | Time | Costs | | Resource / Service | Costs | Service | Costs | Work station | Costs |
| A  N  A  L  Y  S  I  S | **Initial record** | | Project Manager   * Engagement Management * Documenter 1 | | 3 hrs   * 3 hrs * 3 hrs | $ 432.69 MNX   * $ 204.24 MNX * $ 72.09 MNX | | * Lap-top (Compac) * Mouse (Wired) * Sheet of paper * Pen * Print * Table * Chair | $ 24.00 MNX  $ 0.00 MNX  $ 2.00 MNX  $ 1.50 MNX  $ 4.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 1.71 MNX  $ 1.83 MNX  $ 0.48 MNX | * Office (Classroom) * Bathroom | $ 432.69 MNX  $ 0.00 MNX |
| Compilation of requirements | | Project Manager   * Engagement Management * Analyst | | 5 hrs   * 5 hrs * 5 hrs | $ 721.15 MNX   * $340.04 MNX * $ 216.30 MNX | | * Lap-top   (Compac)   * Mouse (Wired) * Sheet of paper * Pen * Print * Table * Chair | $ 40.00 MNX  $ 0.00 MNX  $ 2.00 MNX  $ 1.50 MNX  $ 4.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 2.85 MNX  $ 3.05 MNX  $ 0.80 MNX | * Office (Classroom) * Bathroom * Cafeteria | $ 14.80 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Requirements analysis | | Analyst | | 6 hrs | $ 259.56 MNX | | * Lap-top (Compac) * Mouse (Wired) * Requirements list * Table * Chair | $ 48.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 3.42 MNX  $ 3.66 MNX  $ 0.96 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Formulation of requirements | | Analyst   * Project Manager | | 6 hrs   * 2 hr | $ 259.56 MNX   * $ 288.46 MNX | | * Lap-top (Compac) * Mouse (Wired) * Table * Chair | $ 48.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 3.42 MNX  $ 3.66 MNX  $ 0.96 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Documentation | | Documenter 1 | | 8 hrs | $ 192.24 MNX | | * Lap-top (Compac) * Mouse (Wired) * Table * Chair | $ 48.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 4.56 MNX  $ 4.88 MNX  $ 1.28 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| D  E  S  I  G  N  D  E  S  I  G  N | Technical design of the system | | System architect   * Designer 2 | | 4 hrs   * 5 hrs | $ 384.60 MNX   * $ 139.40 MNX | | * Lap-top (HP) * Mouse * Extension * Requirements list * Table * Chair | $ 32.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 2.28 MNX  $ 2.44 MNX  $ 0.64 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Functional system design | | Designer 1   * Designer 2 | | 4 hrs   * 5 hrs | $ 128.76 MNX   * $ 139.40 MNX | | * Lap-top (Lenovo) * Mouse * Extension * Requirements list * Table * Chair | $ 32.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 2.28 MNX  $ 2.44 MNX  $ 0.64 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Navigation map | | System Architect | | 6 hrs | $ 576.90 MNX | | * Lap-top (HP) * Mouse * Extension * Requirements list * Table * Chair | $ 32.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 3.42 MNX  $ 3.66 MNX  $ 0.96 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Templates | | Designer 1   * Designer 2 | | 4 hrs   * 4 hrs | $ 128.76 MNX   * $ 111.52 MNX | | * Lap-top (Lenovo) * Mouse * Extension * Requirements list * Table * Chair | $ 32.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 2.28 MNX  $ 2.44 MNX  $ 0.64 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| System diagrams | | Designer 1   * Designer 2 | | 4 hrs   * 10 hrs | $ 128.76 MNX   * $ 278.80 MNX | | * Lap-top (HP) * Mouse * Extension * Requirements list * Table * Chair | $ 32.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 2.28 MNX  $ 2.44 MNX  $ 0.64 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Documentation | | Documenter 2 | | 8 hrs | $ 176.88 MNX | | * Lap-top (Lenovo) * Mouse * Table * Chair | $ 64.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 4.56 MNX  $ 4.88 MNX  $ 1.28 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| V  E  R  I  F  I  C  A  T  I  O  N | System design evaluation | | Analyst   * Tester | | 8 hrs   * 6 hrs | $ 346.08 MNX   * $ 366.72 MNX | | * Lap-top (Compac) * Mouse * Extension * Requirements list * Table * Chair | $ 48.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 3.42 MNX  $ 3.66 MNX  $ 0.96 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Evaluation of system components | | Analyst   * Tester | | 8 hrs   * 6 hrs | $ 346.08 MNX   * $ 366.72 MNX | | * Lap-top (Compac) * Mouse * Extension * Requirements list * Table * Chair | $ 48.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 4.56 MNX  $ 4.88 MNX  $ 1.28 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Review of the requirements | | Analyst   * Project Manager | | 8 hrs   * 6 hrs | $ 346.08 MNX   * $865.38 MNX | | * Lap-top (Compac) * Mouse * Extension * Requirements list * Table * Chair | $ 48.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 4.56 MNX  $ 4.88 MNX  $ 1.28 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Documentation | | Documenter 1 | | 8 hrs | $ 192.24 MNX | | * Lap-top (Compac) * Mouse * Table * Chair | $ 64.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 4.56 MNX  $ 4.88 MNX  $ 1.28 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| P  R  O  G  R  A  M  M  I  N  G  ~  +  ~  P  R  O  G  R  A  M  M  I  N  G  ~  +  ~  P  R  O  G  R  A  M  M  I  N  G | Creation of the BD | | System Architect | | 8 hrs | $ 769.20 MNX | | * Lap-top (HP) * Mouse * Extension * Requirements list * System design * Table * Chair | $ 64.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 4.56 MNX  $ 4.88 MNX  $ 1.28 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Module coding Users | | Programmer 1   * Programmer 2 | | 12 hrs   * 12 hrs | $ 1,269.12 MNX   * $ 1,096.08 MNX | | * Lap-top (Compac) * Mouse * Extension * Requirements list * System design * Table * Chair | $ 96.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 6.12 MNX  $ 7.32 MNX  $ 1.92 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Module coding LogIn | | Programmer 1   * Programmer 2 | | 12 hrs   * 12 hrs | $ 1,269.12 MNX   * $ 1,096.08 MNX | | * Lap-top (Compac) * Mouse * Extension * Requirements list * System design * Table * Chair | $ 96.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 6.12 MNX  $ 7.32 MNX  $ 1.92 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Module coding Products | | Programmer 1   * Programmer 2 | | 12 hrs   * 12 hrs | $ 1,269.12 MNX   * $ 1,096.08 MNX | | * Lap-top (HP) * Mouse * Extension * Requirements list * System design * Table * Chair | $ 96.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 6.12 MNX  $ 7.32 MNX  $ 1.92 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Coding of the news module | | Programmer 1   * Programmer 2 | | 12 hrs   * 12 hrs | $ 1,269.12 MNX   * $ 1,096.08 MNX | | * Lap-top (HP) * Mouse * Extension * Requirements list * System design * Table * Chair | $ 96.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 6.12 MNX  $ 7.32 MNX  $ 1.92 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Module coding Contact | | Programmer 1   * Programmer 2 | | 12 hrs   * 12 hrs | $ 1,269.12 MNX   * $ 1,096.08 MNX | | * Lap-top (Compac) * Mouse * Extension * Requirements list * System design * Table * Chair | $ 96.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 6.12 MNX  $ 7.32 MNX  $ 1.92 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Module coding about us | | Programmer 1   * Programmer 2 | | 12 hrs   * 12 hrs | $ 1,269.12 MNX   * $ 1,096.08 MNX | | * Lap-top (Compac) * Mouse * Extension * Requirements list * System design * Table * Chair | $ 96.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 6.12 MNX  $ 7.32 MNX  $ 1.92 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Identification of errors | | Programmer 1   * Tester * Analyst | | 8 hrs   * 6 hrs * 6 hrs | $ 846.08 MNX   * $ 366.72 MNX * $ 259.56 MNX | | * Lap-top (Compac) * Mouse * Extension * Requirements list * System design * Table * Chair | $ 96.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 4.56 MNX  $ 4.88 MNX  $ 1.28 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Debugging errors | | Programmer 1   * Programmer 2 | | 12 hrs   * 12 hrs | $ 1,269.12 MNX   * $ 1,096.08 MNX | | * Lap-top (HP) * Mouse * Extension * Requirements list * System design * Table * Chair | $ 96.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 6.12 MNX  $ 7.32 MNX  $ 1.92 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Error matrix | | Documenter 1 | | 8 hrs | $ 192.24 MNX | | * Lap-top (Compac) * Mouse * Extension * Requirements list * System design * Table * Chair | $ 64.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 4.56 MNX  $ 4.88 MNX  $ 1.28 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Change matrix | | Documenter 2 | | 8 hrs | $ 176.88 MNX | | * Lap-top * Mouse * Extension * Requirements list * System design * Table * Chair | $ 64.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 4.56 MNX  $ 4.88 MNX  $ 1.28 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Documentation | | Documenter 1 | | 8 hrs | $ 192.24 MNX | | * Lap-top (Compac) * Mouse * Table * Chair | $ 64.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 4.56 MNX  $ 4.88 MNX  $ 1.28 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| T  E  S  T  S  ~  +  ~  T  E  S  T  S  ~  +  ~  T  E  S  T  S  ~  +  ~  T  E  S  T  S  ~  +  ~  T  E  S  T  S | Test execution plan | | Analyst   * Tester | | 8 hrs   * 8 hrs | $ 346.08 MNX   * $ 488.96 MNX | | * Lap-top (Hp-1) * Mouse * Extension * Requirements list * System design * Table * Chair | $ 64.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 4.56 MNX  $ 4.88 MNX  $ 1.28 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Errors identification | | Analyst   * Tester | | 8 hrs   * 8 hrs | $ 346.08 MNX   * $ 488.96 MNX | | * Lap-top (Hp-1) * Mouse * Extension * Requirements list * System design * Table * Chair | $ 64.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 4.56 MNX  $ 4.88 MNX  $ 1.28 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| General test | | Analyst   * Tester | | 12 hrs   * 8 hrs | $ 519.12 MNX   * $ 488.96 MNX | | * Lap-top (Compaq) * Mouse * Extension * System design * Table * Chair | $ 96.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 6.12 MNX  $ 7.32 MNX  $ 1.92 MNX | * House (Living room) * Bathroom * Cafeteria | $ 35.52 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Compatibility test | | Analyst   * Tester | | 12 hrs   * 12 hrs | $ 519.12MNX   * $ 733.44 MNX | | * Lap-top (Hp-1) * Mouse * Extension * System design * Table * Chair | $ 64.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 6.12 MNX  $ 7.32 MNX  $ 1.92 MNX | * House (Living room) * Bathroom * Cafeteria | $ 35.52 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Test by module | | Analyst   * Tester | | 12 hrs   * 12 hrs | $ 519.12 MNX   * $ 733.44 MNX | | * Lap-top (Hp-1) * Mouse * Extension * System design * Table * Chair | $ 64.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 6.12 MNX  $ 7.32 MNX  $ 1.92 MNX | * House (Living room) * Bathroom * Cafeteria | $ 35.52 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Implementation | | Project Manager   * Engagement management * Programmer 1 | | 12 hrs   * 12 hrs * 16 hrs | $ 1,730.76 MNX   * $ 816.96 MNX * $ 1,692.12 MNX | | * Lap-top (Hp-1) * Mouse * Extension * System design * Table * Chair | $ 64.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 6.12 MNX  $ 7.32 MNX  $ 1.92 MNX | * House (Living room) * Bathroom * Cafeteria | $ 35.52 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Final functional test | | Analyst   * Tester | | 8 hrs   * 8 hrs | $ 346.08MNX   * $ 488.96 MNX | | * Lap-top (Hp-1) * Mouse * Extension * System design * Table * Chair | $ 32.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 4.56 MNX  $ 4.88 MNX  $ 1.28 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Realization from the matrix of changes | | Documenter 2 | | 8 hrs | $ 176.88 MNX | | * Lap-top (Hp-1) * Mouse * Extension * System design * Table * Chair | $ 64.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 4.56 MNX  $ 4.88 MNX  $ 1.28 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Project closing act | | Documenter 1   * Project Manager * Engagement Management | | 8 hrs   * 4 hrs * 6 hrs | $ 192.24 MNX   * $ 576.92 MNX * $ 408.48 MNX | | * Lap-top (Compac) * Mouse * Table * Chair | $ 64.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 4.56 MNX  $ 4.88 MNX  $ 1.28 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Documentation | | Documenter 1 | | 8 hrs | $ 192.24 MNX | | * Lap-top (Compac) * Mouse * Table   Chair | $ 64.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 4.56 MNX  $ 4.88 MNX  $ 1.28 MNX | * House (Living room) * Bathroom | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Empty in log | | Documenter 2 | | 18 hrs | $ 397.98 MNX | | * Lap-top (Compac) * Mouse * Table * Chair | $ 144.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 10.26 MNX  $ 10.98 MNX  $ 2.88 MNX | * House (Living room) * Bathroom | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| M  A  I  N  T  E  N  A  N  C  E | Correction of errors of use | | Analyst   * Programmer 1 | | 8 Hrs   * 12 hrs | $ 346.08 MNX   * $ 1,269.12 MNX | | * Lap-top (Hp-1) * Mouse * Extension * Error matrix * Table * Chair | $ 64.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 6.12 MNX  $ 7.32 MNX  $ 1.92 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Purification of usage flaws | | Analyst   * Programmer 1 | | 8 Hrs   * 12 hrs | $ 346.08 MNX   * $ 1,269.12 MNX | | * Lap-top (Hp-1) * Mouse * Extension * Error matrix * Table * Chair | $ 64.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 6.12 MNX  $ 7.32 MNX  $ 1.92 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |
| Updating the error matrix | | Documenter 1 | | 8 Hrs | $ 192.24 MNX | | * Lap-top (Hp-1) * Mouse * Extension * Error matrix * Table * Chair | $ 64.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX | * Light * Internet * Water | $ 4.56 MNX  $ 4.88 MNX  $ 1.28 MNX | * House (Living room) * Bathroom * Cafeteria | $ 0.00 MNX  $ 0.00 MNX  $ 0.00 MNX |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Phase | Human Resources | Material resource | Good or service | Total |
| Analysis | $ 2,986.33 | $ 223.00 | $ 26.19 | **$ 3,235.52** |
| Design | $ 2,193.78 | $ 224.00 | $ 29.98 | **$ 2,447.76** |
| Verification | $ 2,829.30 | $ 208.00 | $ 40.12 | **$ 3,077.42** |
| Programming | $ 19,359.32 | $ 1,024.00 | $ 161.12 | **$ 20,544.44** |
| Test | $ 12,202.90 | $ 784.00 | $ 139.16 | **$ 13,126.06** |
| Maintenance | $ 3,422.64 | $ 192.00 | $ 41.44 | **$ 3,656.08** |
| TOTAL AMOUNT | | **$ 46,087.28** | | |

**Referencias**

[Revista Gerencia - Profesionales TIC: ¿Qué busca el mercado?](http://www.emb.cl/gerencia/articulo.mvc?xid=492&edi=119&xit=profesionales-tic-que-busca-el-mercado)www.emb.cl

[Estudio de Sueldos de TI México 2014 - Desarrollo de Carrera Profesionistas TI](http://empleosti.la/blog/estudio-sueldos-ti-mexico-2014/)empleosti.la

Palladino, E. (2014). *Administración y gestión de proyectos*. Retrieved from <https://ebookcentral.proquest.com>

Torres, H. Z., & Torres, M. H. (2014). *Administración de proyectos*. Retrieved from <https://ebookcentral.proquest.com>

Rodríguez, M. A. M. (2005). *Centros de cómputo y administración de proyectos*. Retrieved from <https://ebookcentral.proquest.com>